## Project Planner
[8 empty] | Week 1 |  |  |  |  | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15 | [6 empty] | Week 16 | [6 empty] | Week 17
[40 empty] | Altium Component Library Review | [6 empty] | Schematic Review | [6 empty] | Layout Placement Review |  |  |  |  | Demo IDE Running |  | Layout Routing Review |  |  | Midterm |  |  |  | Final Design Review | [6 empty] | PCB released to fab | [8 empty] | PCB back for assembly | [6 empty] | Fall Break Week | [6 empty] | Assembly Complete | [14 empty] | Midterm 2 (Final) | [6 empty] | Project Demos
|  |  | Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: |  | 26 |  |  | Plan Duration | [5 empty] | Actual Start | [5 empty] | Actual (beyond plan)
Project Planner | [18 empty] | % Complete | [5 empty] | % Complete (beyond plan)
[8 empty] | August 28th |  |  | September 1st | September 2nd | September 3rd | [27 empty] | October 2nd | [29 empty] | November1st | [29 empty] | December 1st | [15 empty] | Finals Week
ACTIVITY | LEAD | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | COMMENTS | PERIODS
[8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117
Project Sensors Selection | Aneesh, Vaishnavi, Devang | 4 | 4 | 4 | 4 | 100%
Heart Rate and Oxygen level Sensors research and selection | Vaishnavi | 4 | 2 | 4 | 2 | 100%
Accerelometer: Sensor study and selection | Devang | 4 | 3 | 5 | 3 | 100%
GPS Module: Study and selection | Aneesh | 4 | 3 | 5 | 3 | 100%
MAX30102 Power consumption analysis | Vaishnavi | 11 | 1 | 11 | 1 | 100%
LIS3DH Power consumption analysis | Devang | 12 | 1 | 12 | 1 | 100%
SAM-M8Q Power consumption analysis | Aneesh | 15 | 1 | 15 | 1 | 100%
Peak average current calculation for the system | Devang | 18 | 1 | 18 | 1 | 100%
Search and finalize energy storage element | Aneesh | 13 | 1 | 13 | 1 | 85%
Search and finalize PMIC | Aneesh | 15 | 1 | 15 | 1 | 50%
Update sensor interface selection and it's reasoning | Vaishnavi | 20 | 1 | 23 | 1 | 100%
Add energy mode breakdown and sensor state analysis. | Devang | 20 | 1 | 23 | 1 | 100%
Update dataflow diagram | Devang | 17 | 1 | 22 | 1 | 100%
Verify analysis of Use-case recharge time requirements | Vaishnavi | 26 | 1 | 0 | 0 | 0%
Verify analysis of sizing storage based on use case number of charge cycles | Aneesh | 26 | 1 | 0 | 0 | 0%
Altium Schematic Library | Aneesh | 27 | 3 | 0 | 0 | 0%
Altium Schematic Library | Vaishnavi | 27 | 3 | 0 | 0 | 0%
Altium Schematic Library | Devang | 27 | 3 | 0 | 0 | 0%
Sensor Interfacing: GPS Module | Aneesh | 27 | 2 | 0 | 0 | 0%
Sensor Interfacing: Heart Rate and SpO2 Module | Vaishnavi | 27 | 2 | 0 | 0 | 0%
Sensor Interfacing: Accelerometer | Devang | 27 | 2 | 0 | 0 | 0%
Verification of sensors: GPS Module | Aneesh | 29 | 1 | 0 | 0 | 0%
Verification of sensors: Heart Rate and SpO2 Module | Vaishnavi | 29 | 1 | 0 | 0 | 0%
Verification of sensors: Accelerometer | Devang | 29 | 1 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%
|  | 0 | 0 | 0 | 0 | 0%